## 90-Day Roadmap
AI Governance Remediation Roadmap
Northgate Family Medicine · Engagement SAL-2026-014 · 90 days from April 22, 2026
Phase | Action | Owner | Effort | Dependencies | Acceptance Criteria | Status | Completion Date
Week 1 | Enable Cisco Umbrella DLP on AI categories | IT | 1 day | — | Umbrella console shows 18 AI-category domains in Block/Monitor state; test query blocked; 90-day log retention configured | Not started
Week 1 | Distribute AUP with required acknowledgment | HR | 3 days | AUP DOCX delivered | TalentLMS shows AUP assigned to 118 employees; acknowledgment rate ≥ 90% within 14 days; receipts exported to HRIS | Not started
Week 1 | Disable ChatGPT consumer access for 4 flagged users | IT | 1 hour | User list from Deliverable 01 | Okta logs show no successful sessions for the 4 users; replacement (Copilot E5) access confirmed | Not started
Week 1 | Initiate Otter.ai Enterprise+ BAA repaper | Procurement | 1 day | — | Otter.ai legal acknowledges request with estimated BAA execution date; clinical leadership notified of migration plan | Not started
Day 30 | Microsoft Copilot E5 rollout to billing and office staff | IT | 2 weeks | Week 1 #1 complete | Department-by-department rollout complete; access verified in Okta entitlement audit; usage telemetry shows displacement of consumer ChatGPT | Not started
Day 30 | Modules 1 + 2 of training delivered | Compliance | 2 weeks | AUP distribution | Module 1 completion ≥ 95%; Module 2 role-track assignment configured and completion ≥ 80% per role | Not started
Day 30 | Otter.ai Enterprise+ BAA executed and seats migrated | Procurement | 2 weeks | Week 1 #4 complete | Executed BAA in compliance vault; 7 seats migrated to Enterprise+; intake protocol updated to reference new tier | Not started
Day 30 | Custom GPT for billing — security review & sanction or sunset | CIO | 1 week | — | CIO decision documented; if sanctioned: BAA-covered API key in place, prompt logging enabled, documented owner; if sunset: replacement workflow defined | Not started
Day 60 | Carrier renewal questionnaire response — submit | CIO | 3 days | All Day-30 items | Questionnaire submitted with Sprint report + Appendix exhibits attached; submission acknowledgment from carrier retained | Not started
Day 60 | Module 3 training delivered | Compliance | 1 week | Module 2 complete | Module 3 completion ≥ 95%; scenario quiz pass rate ≥ 80% | Not started
Day 60 | Sanctioned tool inventory published internally | IT | 2 days | — | Inventory published to intranet with version control; quarterly review cycle calendared | Not started
Day 60 | First quarterly governance committee meeting | CIO | 2 hours | — | Meeting held; minutes captured; AI standing agenda established; next meeting calendared | Not started
Day 90 | Procurement workflow updated for AI vendor review | Procurement | 2 weeks | — | New AI vendor request template live in ticketing system; security review checklist embedded; CIO sign-off required for any vendor processing PHI | Not started
Day 90 | IR runbook AI scenarios tested in tabletop exercise | IT/CIO | 1 day | AI runbook delivered Day 12 | Tabletop conducted with 4 scenarios; gaps documented; runbook revision committed; next test calendared annually | Not started
Day 90 | Module 4 refresh quiz scheduled in LMS | Compliance | 1 day | Module 1-3 complete | Module 4 configured for annual re-acknowledgment on anniversary date; quiz bank rotates 4 versions | Not started
Day 90 | 2027 renewal calendar set with 90-day pre-flight | CIO | 1 hour | Day-60 carrier submission | Calendar entry for Q1 2027 risk assessment kickoff; reminders set 90 / 60 / 30 days before May 2027 renewal | Not started

## Summary
Roadmap Summary
Total actions | 16
Week 1 actions (highest priority) | 4
Day 30 actions | 4
Day 60 actions | 4
Day 90 actions | 4
Status tracking
Not started | 16
In progress | 0
Complete | 0
Completion % | 0%